## Project Plan - Automated Integr
Phase | Meeting | Stage | Days After Start | Duration (Days) | Start | Finish | Predecessors | Assigned To | Description | Help Center Resource
1 Initiation | 1 | 1 Kickoff | 0 | 1 | 2019-12-30 | 2019-12-30 |  | Liaison | Begin the project: determine goals, identify needed resources, and assign responsibilities. | https://help.liaisonedu.com/Data_Integration/Mapping_Out_Your_Data_Integration_Project/01_Planning_for_Data_Integration
1 Initiation | 1 | 2 Assemble Team | 0 | 10 | 2019-12-30 | 2020-01-10 | 1 | Project Lead | Get the people with the skills, knowledge, and access needed to complete the project. | https://help.liaisonedu.com/Data_Integration/Mapping_Out_Your_Data_Integration_Project
1 Initiation | 1 | 3 CAS Onboarding Status | 0 | 5 | 2019-12-30 | 2020-01-03 | 1 | Project Lead | Take stock of the current CAS situation: is the application live or not? | https://help.liaisonedu.com/Data_Integration/Mapping_Out_Your_Data_Integration_Project
1 Initiation | 1 | 4 Use for Data | 0 | 1 | 2019-12-30 | 2019-12-30 | 1 | Admissions | Determine how CAS application data will be used in local systems. | https://help.liaisonedu.com/Data_Integration/Identifying_Uses_for_Your_Data/Using_CAS_Application_Data_After_Loading_it_Locally
1 Initiation | 1 | 5 Integration Timing | 1 | 1 | 2019-12-31 | 2019-12-31 | 4 | Admissions | Determine at what point in the admissions funnel CAS application data will be transferred. | https://help.liaisonedu.com/Data_Integration/Mapping_Out_Your_Data_Integration_Project
1 Initiation | 1 | 6 Integration Frequency | 1 | 1 | 2019-12-31 | 2019-12-31 | 4 | Admissions | Determine how often CAS application data needs to be transferred to local systems. | https://help.liaisonedu.com/Data_Integration/Mapping_Out_Your_Data_Integration_Project
1 Initiation | 1 | 7 Local Systems Assessment | 1 | 4 | 2019-12-31 | 2020-01-03 | 4 | Business Analyst/Developer | Understand how to load data and documents to local systems. | https://help.liaisonedu.com/Data_Integration/Loading_Your_Data/Loading_Data_into_Local_Systems
2 Planning | 1 | 8 Fields Required | 5 | 4 | 2020-01-06 | 2020-01-09 | 7 | Business Analyst | Identify what data points and document types need to be transferred. | https://help.liaisonedu.com/Data_Integration/Extracting_Your_Data
2 Planning | 1 | 9 Source Fields | 9 | 1 | 2020-01-10 | 2020-01-10 | 8 | Business Analyst | Determine where the needed data points and document types are stored in the CAS. | https://help.liaisonedu.com/Data_Integration/Extracting_Your_Data
2 Planning | 1 | 10 Plan Workflow | 5 | 5 | 2020-01-06 | 2020-01-10 | 7 | Business Analyst | Plan how data will flow from CAS into local systems, and determine resources needed. | https://help.liaisonedu.com/Data_Integration/Mapping_Out_Your_Data_Integration_Project
2 Planning | 1 | 11 CAS Configuration | 5 | 5 | 2020-01-06 | 2020-01-10 | 7 | Project Lead | Configure the CAS application for ease of data integration. | https://help.liaisonedu.com/Data_Integration/Collecting_Applicant_Data/Configuring_Your_Programs_for_Ease_of_Data_Integration
2 Planning | 1 | 12 Create Test Data | 5 | 5 | 2020-01-06 | 2020-01-10 | 7 | Admissions | Create test application data to be used in building the integration (if necessary). | https://help.liaisonedu.com/Data_Integration/Mapping_Out_Your_Data_Integration_Project/Testing_Your_Integration
3 Execution | 2 | 13 Build Exports | 10 | 10 | 2020-01-13 | 2020-01-24 | 2, 9 | Business Analyst | Use Liaison's tools to extract CAS application data. | https://help.liaisonedu.com/Data_Integration/Extracting_Your_Data
3 Execution | 3 | 14 Build Transformation | 20 | 10 | 2020-01-27 | 2020-02-07 | 2, 13 | Business Analyst/Developer | Set up process to transform CAS application data to match local system requirements. | https://help.liaisonedu.com/Data_Integration/Transforming_Your_Data/Working_with_Data_Transformations
3 Execution | 3 | 15 Configure Load | 20 | 10 | 2020-01-27 | 2020-02-07 | 2, 13 | Business Analyst/Developer | Configure upload into local system to accommodate CAS application data. | https://help.liaisonedu.com/Data_Integration/Loading_Your_Data
3 Execution | 4 | 16 Build Automation | 30 | 10 | 2020-02-10 | 2020-02-21 | 2, 15 | Developer | Build process to automate the extraction, transformation, and upload of CAS application data. | https://help.liaisonedu.com/Data_Integration/Moving_Your_Data
3 Execution | 4 | 17 Build Quality Control | 30 | 10 | 2020-02-10 | 2020-02-21 | 2, 15 | Business Analyst | Create quality control processes to ensure CAS data application is transferring properly. | https://help.liaisonedu.com/Data_Integration/Implementing_Quality_Control_in_Your_Integration/Planning_Your_Quality_Control_Process
4 Monitoring | 5 | 18 Test Integration | 40 | 10 | 2020-02-24 | 2020-03-06 | 12, 15, 17, 16 | ALL | Test the data integration. | https://help.liaisonedu.com/Data_Integration/Mapping_Out_Your_Data_Integration_Project/Testing_Your_Integration
5 Close | 6 | 19 Backup Plan | 50 | 10 | 2020-03-09 | 2020-03-20 | 18 | Project Lead | Establish a backup plan in case the data integration fails for any reason. | https://help.liaisonedu.com/Data_Integration/Mapping_Out_Your_Data_Integration_Project/Developing_Your_Backup_Plans
5 Close | 6 | 20 Yearly Maintenance | 50 | 10 | 2020-03-09 | 2020-03-20 | 18 | Project Lead | Create a plan for maintaining the data integration over time. | https://help.liaisonedu.com/Data_Integration/Mapping_Out_Your_Data_Integration_Project/Yearly_Maintenance_for_Your_Integrations
5 Close | 7 | 21 Go-live | 60 | 1 | 2020-03-23 | 2020-03-23 | 20 | Project Lead | Turn on the data integration. | https://help.liaisonedu.com/Data_Integration
Formulas:
Days After Start = NETWORKDAYS(F2,[Start])-1
Duration (Days) = NETWORKDAYS([Start],[Finish])